## Sheet1 (hidden)
|  |  | 2019 | [11 empty] | 2020 | [11 empty] | 2021
|  |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov
Conference |  |  | 2019 Feb: RMM; 2019 Aug: WS; 2019 Dec: WS @JPN; 2020 Feb: RMM @JPN; 2020 Mar: BRO; 2020 Jul: WS @BKK; 2020 Dec: WS; 2021 Feb: RMM; 2021 Nov: WS
HR Management System Reform
TW, TPS, TBP | DMDP | #1, #2
#3, #4
Crash Course
Kaizen Activity | NPS/VOC mgmt.
Absorption, CRt, SMS
Branch SGA based on VOC, VOE
India Best Practice DLR Trip | bar: 2019 Mar; 2019 Nov; 2021 Nov
under study
★
★
☆Review
☆'20 Target Setting
☆'20 Target Setting
☆Final @April 9th
☆Mentor pgrm B1 Jun 8-12 @Dubai
☆Crash Course April 7-9 @India
twice a year
☆Start July @India B1: Jun 29-2July
☆Mentor pgrm B2 Jun 15-19 @Dubai
☆Review
☆Review
(Only Jisyuken)
WS
WS
WS
WS
WS
WS
☆Start July @India B1: Jul 6-9
Mid Rep.
Mid Rep.
Final Rep.
Final Rep.

## 03162020 (hidden)
|  |  | 2019 | [11 empty] | 2020 | [11 empty] | 2021
|  |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov
Conference |  |  | 2019 Feb: RMM; 2019 Aug: WS; 2019 Dec: WS @JPN; 2020 Feb: RMM @JPN; 2020 Mar: BRO; 2020 Jul: WS @BKK; 2020 Dec: WS; 2021 Feb: RMM; 2021 Nov: WS
HR Management System Reform
TW, TPS, TBP | DMDP | #1, #2
#3, #4
Crash Course
Kaizen Activity | NPS/VOC mgmt.
Absorption, CRt, SMS
Branch SGA based on VOC, VOE
India Best Practice DLR Trip | bar: 2019 Mar; 2019 Nov
under study
★
★
☆Review
☆'20 Target Setting
☆'20 Target Setting
☆Final @June 3rd
☆Mentor pgrm B1 Jun 15-19 @Dubai
☆Crash Course June 1-3 @India
twice a year
☆Start July @India B2: Jul 13-16
☆Mentor pgrm B2 Jun 22-26 @Dubai
☆Review
☆Review
(Only Jisyuken)
WS
WS
WS
WS
WS
WS
☆Start July @India B1: Jul 6-9
Mid Rep.
Mid Rep.
Final Rep.
Final Rep.

## 05292020 (3)
|  |  | 2019 | [11 empty] | 2020 | [11 empty] | 2021
|  |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Conference |  |  | 2019 Feb: RMM; 2019 Aug: WS; 2019 Dec: WS @JPN; 2020 Feb: RMM @JPN; 2020 Mar: BRO; 2020 Jul: WS @BKK; 2020 Aug: ★Mid-RMM; 2020 Dec: WS; 2021 Feb: RMM; 2021 Jun: WS; 2021 Dec: WS
HR Management System Reform
TW, TPS, TBP | DMDP | #1, #2
#3, #4
UAE (Under Planing)
Crash Course
Kaizen Activity | NPS/VOC mgmt.
Absorption, CRt, SMS
Branch SGA based on VOC, VOE
India Best Practice DLR Trip | bar: 2019 Mar; 2019 Nov
<New> Online Event/Seminer
直近オンラインイベント |  |  | 2019 May: 日程; 2019 Aug: 内容; 2020 Aug: 対象者; 2021 May: 実施者/協力者
①PDCAセミナー |  |  | 2019 May: 6/22-25; 2019 Aug: ・DMDP事前の簡易TPS/TBP勉強として活用予定 ・既にAFMに展開、今回はトライアルで実施; 2020 Aug: 中東部国担室事技職 (10名) +ICT; 2021 May: by MECAORスジットさん
②Lead/Digital Salesセミナー |  |  | 2019 May: 6/25; 2019 Aug: ・昨年のMEBIT WSで一度Leadは実施 ・今回はLead + Digital Sales事例も合わせて実施; 2020 Aug: 各国MEBITチーム (60名) (マネージメント+販売); 2021 May: by US BITチーム(TMNA)
③クラッシュコース（番頭向けTPS/TBPトレーニング） |  |  | 2019 May: 7/6-9 '7/13-16; 2019 Aug: ・DMDPの番頭向けコースとしてアレンジ ・各国番頭に内容・重要性をご理解いただくことが目的; 2020 Aug: 各国番頭クラス、マネジメント (40名) (販売、サービス、人事、Lexus); 2021 May: by TKM HR/販売
④ DMPDコース最終レポート（TPS/TBPコース#1#2ファイナル） |  |  | 2019 May: 7/27-28; 2019 Aug: ・昨年7月からの継続コースであり今回STEP1～STEP8までの最終レポート; 2020 Aug: 各国MEBITチーム (22名) (マネジメント～Mgtクラス); 2021 May: by TKM HR
⑤Mid-RMM Review |  |  | 2019 May: 8/24-9/1; 2019 Aug: ・中東部より事前にプレゼン送付、当日はQ&Aのみ (Sales Award、流出防止に向けた取組み、新モデル議論など); 2020 Aug: 各国番頭クラス、マネジメント (計5-10名程度) (マネジメント＋販売); 2021 May: -
⑥人事制度紹介セミナー |  |  | 2019 May: 2020-09-14; 2019 Aug: ・現在各国困り事、コンサーンを確認、分析中 ・興味ある共通分野をセミナーで紹介、その後個別対応; 2020 Aug: 各国マネジメント (20名程度) (マネジメント、人事); 2021 May: by TMC人開、TKM HR
⑦AFM向けTBP/TPS教育 |  |  | 2019 May: 10月; 2019 Aug: ・AFM SaudさんよりAFMスタッフ向けにTBP/TPSの教育をして欲しい旨リクエスト有 ・TKMとAFMと打合せ実施予定(スケジュール、コンテンツのレベルを確認); 2020 Aug: AFMスタッフ (**名程度) (セールス、サービス、他); 2021 May: by TKM HR
⑧Toyota Digital Marketing Solutions (Lead Management) ワークショップ |  |  | 2019 May: 2020-09-29; 2019 Aug: ・Lead Managementの重要性理解及びスキル向上 ・Lead Generation強化に向けたSocial Media基本運用・広告運用; 2020 Aug: 各国MEBITチーム、デジタル関連スタッフ (30名程度); 2021 May: by TMC販売支援部
⑨上記③クラッシュコースFollow up会議 |  |  | 2019 May: 10月; 2019 Aug: ・7月実施の番頭向けTPS/TBPトレーニングを受講後の取組み事項等確認、意見交換会実施; 2020 Aug: 各国番頭クラス、マネジメント (40名) (販売、サービス、人事、Lexus); 2021 May: by TKM HR/販売
★
★
☆Review
☆'20 Target Setting
☆'20 Target Setting
☆Final @July 27-28
☆Crash Course
B1 6th-9th July
twice a year
☆Start Apr @India B4: Apr 13-16
☆Mentor pgrm Sep 20-24
(Only Jisyuken)
WS
WS
WS
☆Start Apr @India B3: Apr 6-9
Final Rep.
Final Rep.
☆ PSAQ
Jun 14th
Preparation with support of B1 & B2 PDCA
HR Function Support
𝑆𝑒𝑝 14 HR Function Support
twice a year
☆Crash Course B2
13th-16th July
Individual HR Interviews
Best Practice Sharing
①
②
③
④
⑥
∆ TW/TPS
∆ TBP
Follow ups
∆ TBP
Additional
∆ Additional
Session
Lead/Digital Sales
pracitce seminar
PDCA Seminer
PDCA Seminer
TDMS Lead
Management Sep 29
Preparation with support
of B1 & B2PDCA
⑦
⑧
⑨
⑤